## Sheet1
# | Category | Asset | Threat | Vulnerability | Likelihood | Impact | Risk Score | Risk Level | Existing Controls | Proposed Treatment | Risk Owner | Status
1 | Hardware | Laptop | Theft or loss | No disk encryption | 4 | 4 | 16 | 🔴 High | Password login | Enable full-disk encryption & tracking | IT Admin | Open
2 | Software | Web Application | XSS attack | Poor input validation | 3 | 4 | 12 | 🟡 Medium | Basic firewall | Implement input sanitization & WAF | Dev Team | Open
3 | Information | Customer Data | Data breach | Unencrypted storage | 5 | 5 | 25 | 🔴 High | Passwords | Encrypt database + restrict access | Security Team | Open
4 | People | HR Manager | Phishing attack | Lack of awareness training | 4 | 3 | 12 | 🟡 Medium | Email spam filter | Security awareness training | HR Dept | Open
5 | Physical | Data Center | Power outage | No backup generator | 3 | 5 | 15 | 🔴 High | UPS only | Install generator & monitor system | Facility Team | Open
6 | Network | Firewall | Misconfiguration | Weak change control | 3 | 4 | 12 | 🟡 Medium | Review by admin | Implement formal config policy | Network Admin | Open
7 | Third Party | Cloud Provider (AWS) | Data exposure | Misconfigured S3 buckets | 4 | 5 | 20 | 🔴 High | IAM policy | Enable encryption & periodic audit | Cloud Admin | Open
8 | Policy | Backup Plan | Backup failure | No testing of backups | 3 | 5 | 15 | 🔴 High | Weekly backups | Test restores quarterly | IT Security | Open
9 | Information | Source Code | Public repo exposure | Misconfigured Git | 3 | 5 | 15 | 🔴 High | Private repo | Enforce access control & code reviews | DevOps | Open
10 | People | Vendor | Data misuse | Weak contract/NDA | 3 | 4 | 12 | 🟡 Medium | Vendor NDA | Annual compliance review | Procurement | Open
Risk Score = Likelihood × Impact
Range: 1 → 25 Low (1–5) 🟢 Medium (6–12) 🟡 High (13–25) 🔴