## Sheet1
Risk ID | Asset | Risk Description | Risk Level | Treatment Option | Control Measure | Responsible Person | Target Date | Residual Risk | Status | Remarks
1 | Laptop | Theft or loss due to lack of encryption | 🔴 High | Reduce | Encrypt drives, enable tracking software | IT Admin | 2025-12-01 | 🟡 Medium | In Progress | Part of IT hardening policy
2 | Web Application | XSS attack from poor input validation | 🟡 Medium | Reduce | Implement input sanitization & WAF | Dev Team | 2025-11-20 | 🟢 Low | Planned | OWASP Top 10 control
3 | Customer Data | Data breach due to unencrypted storage | 🔴 High | Reduce | Encrypt DB & restrict access | Security Team | 2025-11-25 | 🟢 Low | In Progress | Test after deployment
4 | Data Center | Power outage causing downtime | 🔴 High | Transfer | Install generator & monitor system | Facility Team | 2025-12-10 | 🟢 Low | Planned | Vendor proposal pending
5 | Firewall | Misconfiguration leading to exposure | 🟡 Medium | Reduce | Formal config review policy | Network Admin | 2025-11-30 | 🟢 Low | Open | Add audit checklist
6 | Cloud Provider (AWS) | Misconfigured S3 buckets causing data exposure | 🔴 High | Reduce | Enable encryption & IAM policy review | Cloud Admin | 2025-12-05 | 🟡 Medium | Open | Automate audit
7 | Backup Plan | No testing of backups | 🔴 High | Reduce | Conduct quarterly restore testing | IT Security | 2025-11-22 | 🟢 Low | Planned | Add to SOP
8 | Source Code | Public repo exposure via misconfig Git | 🔴 High | Avoid | Move repos to private, code review policy | DevOps | 2025-11-15 | 🟢 Low | Closed | Verified in audit
9 | Vendor | Data misuse due to weak contract | 🟡 Medium | Transfer | Strengthen NDA & annual review | Procurement | 2025-12-20 | 🟢 Low | Planned | Add legal clause
Treatment Options (ISO 27001): Avoid – Stop the risky activity. Reduce – Implement controls to lower risk (e.g., patching, MFA). Transfer – Outsource or insure the risk. Accept – Acknowledge and monitor the risk.